## Bug Report
Demoblaze.com — Bug Report
URL: https://www.demoblaze.com/ ¦ Testing Type: Manual ¦ Severity: 🔴 Critical 🟠 High 🟡 Medium 🟢 Low
Bug ID | Module | Bug Title | Description | Steps to Reproduce | Expected Result | Actual Result | Severity | Priority | Status | Reported By | Date
BUG-01 | Signup | Sign up with both fields empty does not show validation | When both username and password are left empty and Sign up is clicked, no proper validation message appears. | 1. Open https://www.demoblaze.com/ 2. Click 'Sign up' 3. Leave username & password blank 4. Click 'Sign up' button | Validation alert should appear: 'Please fill in the fields' | No validation — blank alert or incorrect message shown | 🟠 High | High | 🔴 Open | QA Engineer | 2026-05-17
BUG-02 | Signup | Existing username error message is not user-friendly | When registering with an already taken username, the alert message is unclear and inconsistent. | 1. Click 'Sign up' 2. Enter an already registered username 3. Enter any password 4. Click 'Sign up' | Clear message: 'This username is already taken. Please choose another.' | Alert shows raw text: 'This user already exist.' (grammar error, no guidance) | 🟡 Medium | Medium | 🔴 Open | QA Engineer | 2026-05-17
BUG-03 | Login | Login with wrong password shows no specific error | User gets a generic alert when entering wrong password. No differentiation between wrong password and wrong username. | 1. Click 'Log in' 2. Enter valid username 3. Enter wrong password 4. Click 'Log in' | Specific message: 'Incorrect password. Please try again.' | Generic alert shown — user cannot identify if username or password is wrong | 🟠 High | High | 🔴 Open | QA Engineer | 2026-05-17
BUG-04 | Login | Non-existent user login gives misleading alert | Logging in with a username that does not exist triggers an unclear error message instead of 'User not found'. | 1. Click 'Log in' 2. Enter a username that was never registered 3. Enter any password 4. Click 'Log in' | Alert: 'User not found. Please sign up first.' | Alert text is vague and does not guide the user | 🟡 Medium | Medium | 🔴 Open | QA Engineer | 2026-05-17
BUG-05 | Dashboard | Monitors category filter not working | Clicking the 'Monitors' category on the homepage does not load any monitor products. The page stays the same or shows empty content. | 1. Open homepage 2. Click 'Monitors' category link 3. Wait for 3 seconds | Monitor products (e.g., Apple Monitor 24) should be displayed | No products load — content area appears empty after clicking Monitors | 🔴 Critical | High | 🔴 Open | QA Engineer | 2026-05-17
BUG-06 | Dashboard | Pagination Next/Previous buttons not functioning correctly | Clicking Next or Previous buttons does not consistently paginate through the product list. Sometimes no change occurs. | 1. Open homepage 2. Wait for products to load 3. Click 'Next' button 4. Click 'Previous' button | Products should navigate to next/previous page smoothly | Products do not change or page flickers without loading new products | 🟠 High | High | 🔴 Open | QA Engineer | 2026-05-17
BUG-07 | Add to Cart | Product does not appear in cart after being added | After successfully adding a product (alert confirmed), navigating to Cart page shows an empty cart. | 1. Log in 2. Click any product 3. Click 'Add to cart' 4. Accept alert 5. Click 'Cart' in navbar | Added product should be listed in the cart table with name and price | Cart table is empty — product does not appear despite confirmation alert | 🔴 Critical | High | 🔴 Open | QA Engineer | 2026-05-17
BUG-08 | Add to Cart | Multiple products not all appearing in cart | When two different products are added to the cart, only one appears in the cart table. The second product is missing. | 1. Log in 2. Add Product 1 → accept alert → go back 3. Add Product 2 → accept alert 4. Open Cart | Both Product 1 and Product 2 should appear in cart | Only one product appears; the other is missing from the cart | 🟠 High | High | 🔴 Open | QA Engineer | 2026-05-17
BUG-09 | Signup | Password field accepts extremely short passwords | The signup form allows passwords with only 1 character (e.g., 'a') without any warning. No minimum length validation exists. | 1. Click 'Sign up' 2. Enter a valid username 3. Enter password: 'a' (1 character) 4. Click 'Sign up' | Validation message: 'Password must be at least 6 characters' | Account is created successfully with a 1-character password — security risk | 🟡 Medium | Low | 🔴 Open | QA Engineer | 2026-05-17

## Bug Summary
Demoblaze.com — Bug Summary Dashboard
Total Bugs Found: 9 ¦ All Status: Open ¦ Date: May 2026
📊 Bugs by Severity
Severity | Count | Bug IDs | Color Code | Risk Level
🔴 Critical | 2 | BUG-05, BUG-07 | Red | Immediate Fix Required
🟠 High | 3 | BUG-01, BUG-03, BUG-06, BUG-08 | Orange | Fix in Next Release
🟡 Medium | 3 | BUG-02, BUG-04, BUG-09 | Yellow | Fix Soon
🟢 Low | 1 | — | Green | Fix When Possible
📦 Bugs by Module
Module | Bug Count | Bug IDs
Signup | 3 | BUG-01, BUG-02, BUG-09
Login | 2 | BUG-03, BUG-04
Dashboard | 2 | BUG-05, BUG-06
Add to Cart | 2 | BUG-07, BUG-08